## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sridhar Gajula | 2025-08-27 | RAG chatbot retrieval returned irrelevant PDF chunks | M1 | Stephen Philip | Functional Defect | Improved chunking strategy and embedding tuning for better retrieval accuracy | 2025-08-27 | Closed | Retrieval quality improved
2 | Sridhar Gajula | 2025-09-10 | AI troubleshooting agent hallucinated diagnostic steps | M2 | Stephen Philip | Logic Defect | Implemented step-based diagnostic chains with strict input/output validation using Pydantic schemas | 2025-09-10 | Closed | Reduced hallucinations significantly
3 | Sridhar Gajula | 2025-09-24 | Multi-agent fitness tool agents misinterpreted data exchanges | M3 | Stephen Philip | Integration Defect | Standardized inter-agent communication using structured JSON handoff formats | 2025-09-24 | Closed | Smooth multi-agent coordination
4 | Sridhar Gajula | 2025-10-08 | UI integration caused workflow disconnections between agents | M4 | Stephen Philip | Integration Defect | Built unified UI, conducted end-to-end testing, cleaned code, and finalized documentation | 2025-10-08 | Closed | Full system integration completed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others